LANKA TOOL HIRE (PVT) LTD

Stage 2: Planning & Feasibility Report

COMP70066 Software Engineering Principles and Practices

Appendix E - Scenario 1: Tool-Hire Review Portal

| Student | CB No |
| --- | --- |
| Mohomed Shadil | CB018738 |
| Abdullah Suhail | CB010327 |
| Hashan Lakshitha Walauwatta | CB018777 |

| Document Title | Lanka Tool Hire (Pvt) Ltd Portal - Stage 2 Planning & Feasibility Report |
| --- | --- |
| Version | 1.0 |
| Stage / Week Due | Stage 2, Week End 5 |
| Status | Draft for group submission |
| Owner | Project Team (Shadil, Suhail, Walauwatta) |
| Companion File | Lanka_ToolHire_Gantt.xlsx (editable Gantt chart) |

Table of Contents

1. Introduction	3

2. Group Charter	3

2.1 Team Purpose & Objectives	3

2.2 Team Values & Working Agreement	4

2.3 Project Vision	4

2.4 Project Objectives	4

2.5 Stakeholders	4

Internal Stakeholders	4

External Stakeholders	4

2.6 Roles Overview	5

2.7 Decision-Making Process	5

2.8 Conflict Resolution	5

2.9 Communication Norms	5

2.10 Working Agreement / Code of Conduct	5

2.11 Success Criteria	5

2.12 Team Agreement Sign-off	6

3. Initial Project Plan (Gantt Chart)	7

3.1 Key Milestones	7

4. Role & Work Allocation per Person	8

4.1 Primary Roles	8

4.2 Rotating Scrum Master	8

4.3 Stage-by-Stage Work Breakdown	8

5. Intended Project Management Approach	9

5.1 Methodology	9

5.2 Task Allocation & Tracking	9

5.3 Project Tracking	9

6. Meeting Format & Schedule	10

7. Projected Costing	11

8. Risk Assessment	12

8.1 Legal, Ethical, Societal & Environmental Considerations - Summary	13

9. Version Control	14

9.1 Mechanism	14

9.2 Responsibility	14

9.3 Policy	14

10. Change Management System	15

10.1 Mechanism	15

10.2 Responsibility	15

10.3 Policy	15

Appendix: Team	16

1. Introduction

This report satisfies the Stage 2 (Planning & Feasibility) submission for the COMP70066 group assignment, due Week 5. It sets out how the team - Moohmed Shadil, Abdullah Suhail and Hashan Lakshitha Walauwatta - is organised and governed to deliver the Lanka Tool Hire (Pvt) Ltd review and hire portal (Appendix E, Scenario 1). Lanka Tool Hire (Pvt) Ltd is headquartered in Nugegoda, with branches in Colombo, Kandy and Galle. This report covers the eight items required by the module guidance for this Stage 2 submission: Group Charter, Initial Project Plan (Gantt chart), Role & Work Allocation per Person, Intended Project Management Approach, Meeting Format & Schedule, Projected Costing, Risk Assessment (legal, ethical, societal and environmental), and Version Control. Per the module tutor's guidance, the Change Management System is addressed as a separate deliverable and is not included in this report.

2. Group Charter

2.1 Team Purpose & Objectives

To design, build, test and document a working prototype of the Lanka Tool Hire (Pvt) Ltd review and hire portal that meets the requirements of Appendix E, Scenario 1, and to do so in a way that satisfies COMP70066's four module learning outcomes: systematic understanding of software engineering principles; analysis, design, implementation, test and documentation as a small team; understanding of legal, ethical, professional, societal and environmental issues; and individual critical reflection on skills developed.

2.2 Team Values & Working Agreement

- Equal contribution - workload is split as evenly as reasonably possible across all stages (see Section 4), tracked via the Project Management Task Log.

- Transparency - progress, blockers and concerns are raised as soon as they arise, not at the next deadline.

- Punctuality - members attend scheduled meetings on time or give at least 2 hours' notice if unavoidably unavailable.

- Respect for skill differences - members support one another's learning rather than simply redistributing difficult work.

- Constructive feedback - code, design and document reviews focus on the work, not the person.

- Academic integrity - all individually authored contributions are accredited; group work is genuinely co-produced, in line with the module's academic misconduct policy.

2.3 Project Vision

To deliver a user-friendly, secure and reliable online tool-hire review portal that improves customer confidence when hiring equipment by providing transparent pricing, verified customer reviews and an intuitive search experience.

The project also aims to demonstrate professional software engineering practices including Agile development, version control, testing and collaborative teamwork.

2.4 Project Objectives

The project team has identified the following objectives:

- Develop a searchable catalogue containing multiple categories of tool-hire equipment.

- Implement an accurate rental cost calculator capable of calculating hourly, daily and long-term hire charges.

- Allow registered users to submit reviews, ratings and comments.

- Implement an administrator portal to manage equipment, pricing and customer reviews.

- Ensure all reviews are moderated before publication.

- Produce a responsive and user-friendly interface.

- Maintain secure authentication and role-based access control.

- Complete all documentation required for COMP70066.

- Deliver a working prototype by the end of Week 12.

- Demonstrate the completed system during the final assessment.

2.5 Stakeholders

The successful completion of this project depends on communication between several stakeholders.

Internal Stakeholders

| Stakeholder | Responsibility |
| --- | --- |
| Development Team | Design, implementation, testing and documentation |
| Project Supervisor | Academic guidance and assessment |
| Quality Assurance Lead | Test planning, defect verification and quality assurance |

External Stakeholders

| Stakeholder | Responsibility |
| --- | --- |
| Lanka Tool Hire (Pvt) Ltd | Client requiring the review portal; a Pvt Ltd company headquartered in Nugegoda, with branches in Colombo, Kandy and Galle |
| Customers | Search equipment, calculate hire costs and submit reviews |
| System Administrator | Maintain equipment information and moderate customer reviews |

2.6 Roles Overview

Full role and work allocation detail is given in Section 4.  Abdullah Suhail act as the team's primary points of contact with the module tutor and are jointly responsible for consolidating and submitting group deliverables on Blackboard/the course page.

2.7 Decision-Making Process

- Default: consensus, reached through discussion in the weekly Sprint Planning meeting (Section 6).

- If consensus is not reached within one meeting: majority vote (2 of 3).

- Technical disagreements (e.g. a design or library choice): resolved by a timeboxed spike (no more than 1 day) comparing both options against the acceptance criteria, then a team vote.

2.8 Conflict Resolution

- Step 1 - raise the issue directly and privately with the team member concerned.

- Step 2 - if unresolved, raise it as a standing item at the next team meeting for open discussion.

- Step 3 - if still unresolved after 48 hours, escalate to the module tutor for guidance, as a last resort.

2.9 Communication Norms

- Day-to-day updates and quick questions: team WhatsApp/Discord group.

- Scheduled meetings: Microsoft Teams (or in-person on campus when timetables allow).

- Task- and story-level discussion: comments on the relevant GitHub Issue/Project card, so decisions stay attached to the work item.

- Expected response time: within 24 hours on a University working day.

2.10 Working Agreement / Code of Conduct

The project team agrees to:

- Attend scheduled meetings whenever possible.

- Notify the team in advance if unable to attend.

- Complete assigned work before internal deadlines.

- Maintain code quality through peer review.

- Keep GitHub repositories updated regularly.

- Follow Agile Scrum practices throughout development.

- Respect deadlines established within each sprint.

- Contribute equally towards documentation and implementation

2.11 Success Criteria

The project will be considered successful if:

- All mandatory functional requirements have been implemented.

- The rental cost calculator produces accurate results.

- Customers can successfully search and review equipment.

- Administrators can manage tools and moderate reviews.

- Testing demonstrates acceptable software quality.

- All documentation required by COMP70066 has been completed.

- The project is delivered on schedule.

- The prototype is successfully demonstrated during the final presentation.

2.12 Team Agreement Sign-off

By continuing to participate in this project, each team member agrees to the values, roles and processes set out in this Group Charter.

| Developer | Role |  |
| --- | --- | --- |
| Mohomed Shadil | Full Stack | Authentication, Rental Calculator, Testing |
| Abdullah Suhail | Full Stack | Catalogue, Search, Pricing |
| Hashan Lakshitha Walauwatta | Full Stack | Reviews, Moderation, Reporting |

3. Initial Project Plan (Gantt Chart)

Weeks 1-2 (12 and 19 July 2026) - the individual skills matrix/role pitch and the recruitment plan - are already complete. Week 3 (10 August 2026, today) is Group Formation: the skills proforma and signed team contract, submitted alongside this Planning & Feasibility report. The confirmed Phase Two presentation date of 4 October 2026 fixes the far end of the plan, so - rather than the previous buffer week before development began - Sprint 1 now starts this same week: 8 back-to-back one-week sprints (10 Aug - 4 Oct 2026, detailed in the team's Product Backlog & Sprint Plan) run in parallel with Stage 3 (Requirements & Design) documentation and Stage 4 (Implementation & Completion), so that Sprint 8 and the Phase Two demonstration land exactly on the confirmed date. This is a tighter schedule than originally planned, with less slack if a sprint slips; see Section 8 (R1, R2) for the corresponding schedule risk and mitigation.

The full plan is maintained as a live, editable spreadsheet - Lanka_ToolHire_Gantt.xlsx - included alongside this report. Changing any task's Start Week, Duration or Category in that workbook automatically moves and recolours its bar (via Excel conditional formatting), so the plan can be re-baselined as the project progresses. A snapshot is shown below.

Figure 1: Initial Project Plan snapshot (see Lanka_ToolHire_Gantt.xlsx for the live, editable version).

3.1 Key Milestones

| 2 | Stage 0 (25 Jul 26) | Individual skills matrix, role pitch and recruitment plan submitted. |
| --- | --- | --- |
| 3 | Stage 1 (16 Aug 26) | Group formed; skills proforma and signed team contract submitted. |
| 5 | Stage 2 (16 Aug 26) | This Planning & Feasibility report and Gantt chart submitted; Sprint 1 begins. |
| 9 | Stage 3 (13 Sep 26) | Requirements, functional/interface/DB design and test plan submitted; Sprint 5 (calculator) reviewed. |
| 12 | Stage 4 (4 Oct 26) | Implementation & Completion submission: logs, user guide, DB schema, final costings; Sprint 8 reviewed. |
| 13 | Phase Two (4 Oct 26) | Live demonstration and Q&A on specification, design, implementation and test. |

4. Role & Work Allocation per Person

With a team of three, each member holds one primary technical role and one process-ownership role, and all three contribute to every sprint's dev, review and documentation work. Scrum Master duties rotate every sprint (Section 4.2) so each member gains planning/facilitation experience for their individual reflective report.

4.1 Primary Roles

| Member | Role | Responsibilities |
| --- | --- | --- |
| Mohmed Shadil | Full Stack Developer | Authentication,Rental Calculator, Testing |
| Abdullah Suhail | Full Stack Developer | Catalogue, Search, Pricing |
| Hashan Lakshitha Walauwatta | Full Stack Developer | Reviews,Moderation, Reporting |

4.2 Rotating Scrum Master

| Sprint | Scrum Master | Sprint | Scrum Master |
| --- | --- | --- | --- |
| 1 | Mohmed Shadil | 5 | Hashan Lakshitha Walauwatta |
| 2 | Abdullah Suhail | 6 | Moohmed Shadil |
| 3 | Hashan Lakshitha Walauwatta | 7 | Abdullah Suhail |
| 4 | Mohmed Shadil | 8 | Hashan Lakshitha Walauwatta |

The Scrum Master for a given sprint facilitates that sprint's planning, stand-ups and review/retrospective, and updates the burndown tracker (Section 5.3); they do not stop contributing technically.

4.3 Stage-by-Stage Work Breakdown

| Stage |  |  |  |
| --- | --- | --- | --- |
| Stage 0-1 (Wk 1-3) | Skills matrix, role pitch drafting | Recruitment plan, contract drafting | Skills proforma consolidation |
| Stage 2 (Wk 4-5) | Version control & PM approach sections, Gantt build | Change management & meeting schedule sections | Risk assessment & costing sections |
| Stage 3 (Wk 5-9) | Functional design, DB design, backend build (Sprints 1,3,5) | Interface design, front-end build (Sprints 2,4) | Test plan authoring, moderation/reviews build (Sprints 5-6 support) |
| Stage 4 (Wk 10-12) | Final DB schema & costings, backend hardening | User guide, front-end polish, deployment docs | Test execution (unit/cross-browser/UAT), documentation consolidation |
| Phase Two (Wk 13) | Demo: architecture & data walkthrough | Demo: live walkthrough of the portal UI | Demo: test evidence and Q&A support |

5. Intended Project Management Approach

5.1 Methodology

The team will follow Scrum exclusively (no hybrid Kanban/Waterfall elements), run as one-week sprints across Weeks 5-12 (see the Product Backlog & Sprint Plan for the full 8-sprint breakdown, epics and story detail), using a Sprint Backlog board for day-to-day task flow within each sprint. Scrum was chosen over a plan-driven (Waterfall) approach because the scenario's scope was partly left to the team to interpret (categories, review criteria), which favours iterative delivery and regular re-prioritisation over a fixed up-front plan; a short, fixed-length prototype project also benefits from Scrum's frequent, demonstrable increments, which map naturally onto the module's staged submissions.

5.2 Task Allocation & Tracking

- Tool: GitHub Projects (Scrum/Sprint board) linked to the code repository, with columns Sprint Backlog - To Do - In Progress - In Review - Done.

- Every user story from the Product Backlog is entered as a GitHub Issue, labelled with its Epic (A-P), MoSCoW priority and story-point estimate.

- Stories are pulled into a sprint's 'To Do' column during that sprint's planning meeting, sized against known velocity (see 5.3).

- A story only moves to 'Done' when it meets the Definition of Done (peer-reviewed, tested, documented).

5.3 Project Tracking

- Sprint velocity (points completed) is recorded at each sprint review and compared to points planned, to re-baseline later sprints - flagged as a risk in Section 8 if velocity runs persistently below plan.

- A simple burndown (points remaining vs. days elapsed) is updated by that sprint's Scrum Master and shared in the team channel every 2-3 days.

- The Project Management Task Log (a Stage 4 deliverable) records actual hours/effort per member per week against the plan in Section 4.3, supporting both the group's accountability and each member's individual reflective report.

- Blockers/risks raised in a stand-up are logged against the risk register (Section 8) if they are not resolved same-day.

5.4 User Story Point Estimation Method & Justification

Story points are a relative, unit-less measure of the effort, complexity and uncertainty in delivering a user story - not an estimate of hours or days - used consistently across all 80 stories in the Product Backlog (251 points total across 16 epics; see the Product Backlog & Sprint Plan, Section 9).

Every story is sized by the whole team using Planning Poker against a modified Fibonacci scale (1, 2, 3, 5, 8), following this process:

- The story and its acceptance criteria are read aloud and questions are answered before any estimate is given.

- Each member privately selects a point value; no one speaks first, so early opinions cannot anchor the others.

- All three estimates are revealed at the same time. If they match or are adjacent on the scale (e.g. 3 and 5), the higher value is taken and the story moves on.

- If estimates diverge by more than one step, the highest and lowest estimator briefly explain their reasoning and the team re-votes, for a maximum of two rounds, before settling by discussion.

- Estimates are calibrated against agreed reference stories fixed at the first estimation session: 1-2 points = a trivial UI or configuration change (e.g. displaying a static policy page); 3 points = a standard, well-understood CRUD feature (e.g. managing equipment categories); 5 points = a feature with real business logic or multiple states (e.g. the review moderation workflow); 8 points = a complex feature with significant logic and edge cases (e.g. the rental cost calculator, Epic E).

- The agreed value is recorded against the story's GitHub Issue alongside its Epic and MoSCoW priority (Section 5.2), and summed per sprint to give the planned points shown in the Sprint Plan Overview and to compute velocity for the burndown tracker (Section 5.3).

Modified Fibonacci Planning Poker was chosen, rather than estimating in hours or using a formal model such as COCOMO or function-point analysis, for five reasons. First, people size relative effort more reliably than they predict absolute duration, particularly here where the scenario's scope was partly left for the team to interpret (Section 2.4) and true effort is unknown until a story is attempted; this is well established in Agile estimation practice (Cohn, 2005) and underlies the Scrum framework the team has adopted (Section 5.1). Second, the widening gaps in the sequence (1, 2, 3, 5, 8) deliberately mirror how uncertainty grows faster than size: a story that does not fit comfortably on the scale is a signal to split it, which is how several oversized candidate stories were broken down into smaller, INVEST-compliant stories during backlog refinement (Section 6.1). Third, Planning Poker's simultaneous private reveal removes the anchoring bias a single estimator or open round-table discussion would introduce, and turns every disagreement into a short knowledge-sharing exercise - valuable given the team's rotating Scrum Master (Section 4.2) and shared full-stack responsibilities (Section 4.1). Fourth, it is fast enough for a three-person team to size the whole 80-story backlog in a single session, unlike heavier models that assume stable requirements or historical productivity data the team does not have at this stage. Fifth, because every story carries a numeric point value, planned versus completed points per sprint (23-36 across Sprints 1-8; see the Sprint Plan) can be compared directly to track velocity, drive the burndown chart, and flag schedule risk early enough to reprioritise Could-priority stories (Section 8, R2) - which a purely qualitative Small/Medium/Large scheme would not support.

References: Cohn, M. (2005) Agile Estimating and Planning. Upper Saddle River, NJ: Prentice Hall; Schwaber, K. and Sutherland, J. (2020) The Scrum Guide.

6. Meeting Format & Schedule

| Kick-off | Once (Wk 1) | 60 min | In person / Teams | Agree Group Charter, roles and working agreement. |
| --- | --- | --- | --- | --- |
| Sprint Planning | Weekly (Sat) | 30-45 min | Microsoft Teams | Select stories for the sprint; confirm owner and Scrum Master. |
| Stand-up | 2x/week (Wed, Fri) | 10-15 min | WhatsApp async or quick call | What's done, what's next, any blockers. |
| Sprint Review & Retro | Weekly (Fri) | 45 min | Microsoft Teams | Demo completed work; agree Done vs. carried-over; one keep/one change for next sprint. |
| Ad hoc pairing | As needed | Variable | In person / screen-share | Joint debugging, design discussion, unblocking a story. |

Minutes are taken by that sprint's Scrum Master (Section 4.2) using a standard template - Date, Attendees, Decisions, Actions (owner + due date), Next Meeting - and stored in the repository's /docs/meetings folder as the Team Meeting Log (a Stage 4 deliverable).

7. Projected Costing

As a coursework prototype, no real money changes hands; costing is notional, intended to demonstrate the team's ability to estimate effort and infrastructure cost as they would for a real client engagement. Costs are presented in Sri Lankan Rupees (LKR) to reflect the local context of the client, Lanka Tool Hire (Pvt) Ltd, and are broken down across resource planning and effort estimation, sprint-by-sprint direct labour cost, infrastructure/hosting/tooling cost, and the total project budget including contingency.

Labour is costed using a blended full-stack developer rate benchmarked against local associate-level market rates. Final costs will be reconciled against actual effort logged in the Project Management Task Log at Stage 4.

7.1 Resource Planning & Effort Estimation

- Project Duration: 8 Weeks (Sprints 1–8 across Weeks 5–12)

- Development Team: 3 Full-Stack Developers – Mohmed Shadil, Abdullah Suhail and Hashan Lakshitha Walauwatta

- Weekly Commitment: 20 hours per developer / week (60 person-hours per week)

- Total Project Effort: 8 weeks × 3 developers × 20 hrs/week = 480 person-hours

- Standard Hourly Rate: LKR 1,500.00 / hour (Associate / Full-Stack Developer baseline rate)

7.2 Direct Labour Cost Breakdown (Sprint by Sprint)

Labour cost is distributed proportionally based on story point complexity (total 251 story points):

| Sprint | Focus Area / Epics | Story Points | Share (%) | Person-Hours | Sprint Cost (LKR) |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Account & Staff Foundations (A, M, O) | 33 | 13.1% | 63.1 hrs | LKR 94,650.00 |
| Sprint 2 | Equipment Catalogue & Media (J, L) | 23 | 9.2% | 44.0 hrs | LKR 66,000.00 |
| Sprint 3 | Pricing Rules & Browsing (K, B) | 27 | 10.8% | 51.6 hrs | LKR 77,400.00 |
| Sprint 4 | Detail Pages & Search Engine (D, C) | 33 | 13.1% | 63.1 hrs | LKR 94,650.00 |
| Sprint 5 | Rental Cost Calculator (E) | 29 | 11.6% | 55.5 hrs | LKR 83,250.00 |
| Sprint 6 | Reviews, Ratings & Comments (F, G) | 36 | 14.3% | 68.8 hrs | LKR 103,200.00 |
| Sprint 7 | Company Responses & Moderation (H, I, J5) | 36 | 14.3% | 68.8 hrs | LKR 103,200.00 |
| Sprint 8 | Reporting, Testing & Release (N, P) | 34 | 13.5% | 65.1 hrs | LKR 97,650.00 |
| Total | All 16 Epics (A–P) | 251 | 100.0% | 480.0 hrs | LKR 720,000.00 |

| Item / Resource | Description & Paid Plan Tier | Monthly Cost (LKR) | 2-Month Total (LKR) |
| --- | --- | --- | --- |
| Cloud Hosting & Serverless APIs | Vercel Pro / Render Starter Deployment Tier | LKR 7,500.00 | LKR 15,000.00 |
| Managed Database Instance | Managed PostgreSQL (Supabase / Neon DB Pro Plan) | LKR 9,500.00 | LKR 19,000.00 |
| Transactional Email API | SendGrid / Mailgun (Standard Tier for verification & auth) | LKR 5,000.00 | LKR 10,000.00 |
| Cloud Media Storage (S3 / CDN) | AWS S3 / Cloudinary (Product images & assets) | LKR 4,000.00 | LKR 8,000.00 |
| Custom Domain & SSL | 1-Year Commercial .com Domain with SSL Certificate | — | LKR 6,000.00 |
| Project Management & CI/CD | GitHub Team & CI/CD Build Minutes (3 Seats) | LKR 4,500.00 | LKR 9,000.00 |
| Subtotal (Operational / Infrastructure) |  |  | LKR 67,000.00 |

7.3 Infrastructure, Hosting, Database & Tooling Costs (2-Month Duration)

7.4 Total Estimated Project Budget

| Budget Category | Calculation Basis | Amount (LKR) | Share (%) |
| --- | --- | --- | --- |
| Direct Labour Cost | 3 Full-Stack Developers × 480 Hours @ LKR 1,500/hr | LKR 720,000.00 | 83.1% |
| Infrastructure, Hosting & Paid Tooling | Commercial Cloud & API Services (2 Months) | LKR 67,000.00 | 7.7% |
| Contingency Reserve (10%) | 10% Buffer for scope expansion & technical risks | LKR 78,700.00 | 9.2% |
| Grand Total (Estimated Project Budget) |  | LKR 865,700.00 | 100.0% |

8. Risk Assessment

Risks are scored Likelihood (1-5) x Impact (1-5) = Score, rated Low (1-6), Medium (7-14) or High (15-25). The register explicitly covers legal, ethical, societal and environmental considerations alongside the usual technical/schedule/people risks, as required by the module guidance.

| R1 | Team member illness or unavailability reduces sprint capacity | People | 3 | 3 | 9 | Med | Cross-training via pairing; roles documented so any member can cover another's story; rotating Scrum Master spreads PM knowledge (All) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R2 | Scope creep beyond the agreed prototype boundary (Section 2, backlog Section 2) | Schedule | 3 | 3 | 9 | Med | MoSCoW-prioritised backlog; new scope goes through the team’s Change Management process, tracked as a separate deliverable (Suhail) |
| R3 | Defamatory, abusive or fraudulent customer reviews get published | Legal - Defamation Act 2013 / Consumer Rights Act 2015 | 3 | 5 | 15 | High | Mandatory moderation before publication (Epic I); ToS/review policy acceptance at registration (Walauwatta) |
| R4 | Customer or staff personal data mishandled or breached | Legal - UK GDPR / Data Protection Act 2018 | 2 | 5 | 10 | Med | Data minimisation, hashed passwords, explicit consent capture, right-to-erasure (Story A8) (Shadil) |
| R5 | Fake or incentivised reviews distort a tool's rating | Ethical | 3 | 3 | 9 | Med | Moderator guidelines, user flagging, monitoring for review-bombing patterns (Walauwatta) |
| R6 | Rating/ranking formula perceived as biased or gameable | Ethical | 2 | 3 | 6 | Low | Transparent, published rating formula (Section 5, backlog); moderator oversight of outlier reviews (Walauwatta) |
| R7 | Customers without reliable internet/modern devices are excluded | Societal | 2 | 3 | 6 | Low | Lightweight, responsive design (Story B5); no mandatory heavy client-side frameworks (Suhail) |
| R8 | Front end fails to meet accessibility needs of disabled users | Legal - Equality Act 2010 / Societal | 2 | 4 | 8 | Med | WCAG 2.1 AA acceptance criteria built into the Definition of Done (Suhail) |
| R9 | Cloud hosting/data transfer has an avoidable carbon footprint | Environmental | 3 | 2 | 6 | Low | Prefer a hosting provider using renewable energy where cost allows; compress/optimise images (Story L1) to cut data transfer (Shadil) |
| R10 | Uncommitted or lost work due to version control conflicts | Technical | 2 | 3 | 6 | Low | Branching policy, small frequent commits, mandatory PR review (Section 9) (Shadil) |
| R11 | Requirement or design changes made without impact assessment | Process | 3 | 3 | 9 | Med | All changes routed through the team’s Change Management System, tracked as a separate deliverable (Suhail) |
| R12 | Vulnerable third-party library/dependency introduces a security flaw | Technical | 2 | 4 | 8 | Med | Dependency audit (e.g. npm audit) before each sprint release; pin dependency versions (Shadil) |
| R13 | Over-reliance on one member's specialist knowledge (key-person risk) | People | 2 | 3 | 6 | Low | Pair programming rotation; all non-trivial decisions documented in the repository wiki (All) |

8.1 Legal, Ethical, Societal & Environmental Considerations - Summary

Legal: UK GDPR/Data Protection Act 2018 (customer and staff personal data), the Defamation Act 2013 and Consumer Rights Act 2015 (published reviews), and the Equality Act 2010 (accessibility) are the primary legal frameworks engaged by this system (R3, R4, R8).

Ethical: the review and rating system must be fair and resistant to manipulation, and moderation decisions must be applied consistently and transparently to both customer content and the company's own responses (R5, R6).

Societal: the portal must remain usable by customers with older devices, limited connectivity, or disabilities, so as not to exclude any group of Lanka Tool Hire (Pvt) Ltd's customer base from comparing and hiring equipment (R7, R8).

Environmental: tool hire is inherently more sustainable than single-use tool purchase (shared use reduces embodied carbon and e-waste), which the team sees as a positive angle for the business; the team's own environmental responsibility is to keep the portal's hosting and data footprint proportionate (R9).

9. Version Control

9.1 Mechanism

Git, hosted on a private GitHub repository. Branch strategy:

- main - always demonstrable/deployable; protected, no direct pushes.

- dev - integration branch; sprint work merges here first.

- feature/<epic-id>-<short-description> - one branch per user story or small group of related stories (e.g. feature/E-cost-calculator).

- dev is merged into main at the end of each sprint, once that sprint's stories meet the Definition of Done.

9.2 Responsibility

- Repository owner/administrator: Abdullah Suhail- manages repository settings, branch protection rules and collaborator access.

- Each member is responsible for their own feature branches and for raising a Pull Request (PR) promptly once a story is ready for review.

- At least one other team member must review and approve a PR before it is merged into dev.

9.3 Policy

- Commit messages follow the Conventional Commits style: feat:, fix:, docs:, test:, chore: followed by a short description.

- No force-pushing to main or dev.

- A .gitignore excludes dependencies, build artefacts and any secrets/credentials; no credentials are ever committed.

- The repository is tagged at each sprint end (v0.1 ... v0.8) so any point in the project can be recovered.

- Each member keeps a local clone as an informal backup in addition to GitHub's hosted copy.

- A Version Control Log (Stage 4 deliverable) records tags, merge dates and what each release contains.

Appendix: Team

| Moohmed Shadil | CB018738 |
| --- | --- |
| Abdullah Suhail | CB010327 |
| Hashan Lakshitha Walauwatta | CB018777 |

Module: COMP70066 Software Engineering Principles and Practices. Scenario: Appendix E, Scenario 1 (Lanka Tool Hire (Pvt) Ltd).